## Cover Page
HIPAA COMPLIANCE ASSESSMENT
HIPAA Security Rule
Gap Assessment
White Plains Hospital — Governance, Risk & Compliance Program
DOCUMENT INFORMATION
Prepared By | Nadhir Choudhury — GRC Analyst
Organization | White Plains Hospital — White Plains, New York
Document Title | HIPAA Security Rule Gap Assessment
Assessment Scope | All ePHI systems and safeguards — Administrative, Physical, and Technical
Framework | HIPAA Security Rule (45 CFR Part 164, Subpart C)
Version | 1.0 — Initial Assessment
Date | April 2026
Classification | CONFIDENTIAL — Internal Use Only
Next Review | April 2027 — Annual
Approved By | Chief Information Security Officer (CISO)
ASSESSMENT OVERVIEW
Total Requirements Assessed | Requirements Met | Partially Met | Not Met | Critical Gaps | Compliance Score (Strict: Met only)
36 | 0 | 27 | 9 | 13 | 0% strict / 37.5% weighted
REQUIREMENTS BY SAFEGUARD CATEGORY
Safeguard Category | Total | Met | Partial | Not Met | Critical | Score
Administrative Safeguards §164.308 | 20 | 0 | 15 | 5 | 9 | 37.5% wtd
Physical Safeguards §164.310 | 5 | 0 | 3 | 2 | 0 | 30.0% wtd
Technical Safeguards §164.312 | 8 | 0 | 8 | 0 | 3 | 50.0% wtd
Organizational §164.314 | 1 | 0 | 0 | 1 | 1 | 0% wtd
Policies & Procedures §164.316 | 2 | 0 | 1 | 1 | 0 | 25.0% wtd
📌 SCORING NOTE: "0%" = strict methodology counting only fully Met controls (0/36). Weighted methodology (Met=100%, Partial=50%, Not Met=0%) gives 37.5% overall compliance. By safeguard: Admin 37.5% ¦ Physical 30% ¦ Technical 50% ¦ Organizational 0% ¦ Policies 25%. All controls in "Partially Met" status confirm that processes EXIST but are incomplete. Target: 80% weighted compliance by Q3 2026.
DISCLAIMER
This document was created for educational and portfolio demonstration purposes only. All findings, gaps, and scenarios are fictional. This does not represent the actual HIPAA compliance posture of White Plains Hospital and should not be used in any real production or regulatory environment.
CONFIDENTIAL ¦ White Plains Hospital GRC Program ¦ Version 1.0 ¦ April 2026

## Gap Assessment
WHITE PLAINS HOSPITAL ¦ HIPAA SECURITY RULE GAP ASSESSMENT ¦ April 2026
✅ MET — Requirement fully satisfied |  | ⚠️ PARTIALLY MET — Gaps exist |  | ❌ NOT MET — Requirement not addressed |  | Required = Mandatory ¦ Addressable = Risk-based |  | Use Ctrl+F to search ¦ Filters enabled on Row 5
HIPAA Section | Req Type | Control Name | Requirement Description | Current State at WPH | Compliance Status | Gap Identified | Recommended Remediation | Priority | Responsible Owner | Target Date | % Complete
ADMINISTRATIVE SAFEGUARDS ¦ 45 CFR §164.308
§164.308(a)(1) | Required | Security Management Process | Implement policies and procedures to prevent, detect, contain, and correct security violations. | Basic security policies exist but are not formally documented or regularly reviewed. | Partially Met | Formal security management program not established. No documented policy review schedule. | Establish formal security management program. Document all policies. Create quarterly review schedule. | Critical | CISO / GRC Analyst | May 2026 | 10%
§164.308(a)(1)(ii)(A) | Required | Risk Analysis | Conduct an accurate and thorough assessment of potential risks and vulnerabilities to ePHI. | No formal documented risk assessment has been conducted in the past 12 months. | Not Met | HIPAA requires annual documented risk analysis. No current risk assessment document exists. | Conduct formal annual risk assessment. Document findings in risk register. Report to leadership. | Critical | GRC Analyst | April 2026 | 0%
§164.308(a)(1)(ii)(B) | Required | Risk Management | Implement security measures sufficient to reduce risks and vulnerabilities to a reasonable level. | Some ad hoc security measures in place but no formal risk treatment plan or tracking. | Partially Met | Risk treatment plans are not formally documented or tracked. No risk register maintained. | Create and maintain formal risk register. Document treatment plans for all identified risks. | Critical | GRC Analyst | May 2026 | 10%
§164.308(a)(1)(ii)(C) | Required | Sanction Policy | Apply appropriate sanctions against workforce members who fail to comply with security policies. | HR disciplinary policy exists but does not specifically address ePHI security violations. | Partially Met | Sanction policy does not specifically cover ePHI violations or define escalating consequences. | Update HR disciplinary policy to include specific ePHI security violations and tiered consequences. | High | HR Manager / GRC Analyst | June 2026 | 10%
§164.308(a)(1)(ii)(D) | Required | Information System Activity Review | Implement procedures to regularly review records of information system activity. | Epic EHR audit logs are enabled but not reviewed on a regular scheduled basis. | Partially Met | No formal schedule for reviewing audit logs. Access anomalies not being detected proactively. | Implement monthly audit log review process. Assign Privacy Officer responsibility. Create review template. | High | Privacy Officer | May 2026 | 10%
§164.308(a)(2) | Required | Assigned Security Responsibility | Identify the security official responsible for developing and implementing security policies. | CISO role exists but GRC-specific responsibilities are not formally documented. | Partially Met | Security responsibility exists at CISO level but analyst-level GRC responsibilities not formally assigned. | Document formal security responsibility assignments. Establish GRC Analyst role with defined responsibilities. | Medium | CISO | May 2026 | 10%
§164.308(a)(3)(i) | Required | Workforce Authorization and Supervision | Implement procedures for authorization and supervision of workforce members who work with ePHI. | Managers provide verbal authorization for system access. No formal written authorization process. | Partially Met | No formal written authorization process for ePHI access. Access approvals not documented. | Implement formal written access authorization process. Document all ePHI access approvals. | High | IT Manager / HR Manager | June 2026 | 10%
§164.308(a)(3)(ii)(A) | Addressable | Authorization and Supervision | Implement procedures for authorizing access to ePHI consistent with job responsibilities. | Access is assigned by IT based on job title but no formal role-based access matrix exists. | Partially Met | No formal access matrix mapping job roles to required ePHI access levels. | Create role-based access control matrix. Map each job role to minimum necessary access level. | High | IT Manager | June 2026 | 10%
§164.308(a)(3)(ii)(B) | Addressable | Workforce Clearance Procedure | Implement procedures to determine that workforce members access is appropriate. | Background checks conducted at hiring but no ongoing clearance review process. | Partially Met | No periodic re-verification of workforce access appropriateness after initial hire. | Implement quarterly user access reviews. Verify access remains appropriate for current job function. | Medium | HR Manager / IT Manager | July 2026 | 10%
§164.308(a)(3)(ii)(C) | Addressable | Termination Procedures | Implement procedures for terminating access when employment ends. | IT account deactivation is manual and sometimes delayed. No formal offboarding checklist. | Partially Met | Former employee accounts not consistently deactivated at termination. No documented procedure. | Create formal IT offboarding checklist. Automate account deactivation. Audit monthly for orphaned accounts. | High | IT Manager / HR Manager | May 2026 | 10%
§164.308(a)(4)(i) | Required | Information Access Management | Implement policies and procedures for authorizing access to ePHI. | Access management policies exist but are not formally documented with clear authorization requirements. | Partially Met | Information access management policy lacks specificity on ePHI authorization requirements. | Document comprehensive information access management policy with ePHI-specific requirements. | High | Privacy Officer / GRC Analyst | June 2026 | 10%
§164.308(a)(4)(ii)(B) | Addressable | Access Authorization | Implement policies and procedures for granting access to a workstation, transaction, or ePHI. | Access authorization is informal and undocumented. Approvals given verbally by managers. | Not Met | No formal documented access authorization workflow for ePHI systems. | Implement formal access request and authorization workflow with documented approvals and review. | High | IT Manager | June 2026 | 0%
§164.308(a)(5)(i) | Required | Security Awareness and Training | Implement a security awareness and training program for all workforce members. | Annual HIPAA training is conducted but cybersecurity-specific awareness training is lacking. | Partially Met | Training program does not cover current threats including phishing, ransomware, and social engineering. | Expand training program to include cybersecurity awareness. Add phishing simulation exercises quarterly. | Critical | HR Manager / GRC Analyst | May 2026 | 10%
§164.308(a)(5)(ii)(B) | Addressable | Protection from Malicious Software | Implement procedures for guarding against, detecting, and reporting malicious software. | Basic antivirus installed on workstations. No EDR solution. Staff awareness of malware is low. | Partially Met | Antivirus is basic and outdated on some devices. No advanced endpoint detection in place. | Deploy enterprise EDR solution. Implement malware awareness in training program. Establish reporting procedure. | Critical | IT Manager | June 2026 | 10%
§164.308(a)(5)(ii)(C) | Addressable | Log-in Monitoring | Implement procedures for monitoring log-in attempts and reporting discrepancies. | Epic EHR logs login attempts but no monitoring for unusual patterns or failed attempts. | Partially Met | No automated alerting for suspicious login patterns or after-hours access. | Configure automated alerts for failed login attempts and after-hours access. Assign monitoring owner. | High | IT Manager | June 2026 | 10%
§164.308(a)(5)(ii)(D) | Addressable | Password Management | Implement procedures for creating, changing, and safeguarding passwords. | Password policy exists on paper but technical enforcement is inconsistent across systems. | Partially Met | Password complexity and expiration not technically enforced on all hospital systems. | Enforce password policy technically on all systems. Implement MFA. Deploy enterprise password manager. | Critical | IT Manager | May 2026 | 10%
§164.308(a)(6)(i) | Required | Security Incident Procedures | Implement policies and procedures to address security incidents. | No formal written incident response plan exists. Incidents handled informally by IT. | Not Met | No documented incident response plan. Staff do not know escalation procedures. | Develop formal incident response plan. Define roles, procedures, and communication protocols. Conduct tabletop exercise. | Critical | GRC Analyst / CISO | May 2026 | 0%
§164.308(a)(7)(i) | Required | Contingency Plan | Establish policies and procedures for responding to emergency operations and protecting ePHI. | No formal business continuity or disaster recovery plan exists for ePHI systems. | Not Met | No documented contingency plan. No defined RTO or RPO. Backup procedures untested. | Develop contingency plan with defined RTO and RPO. Document backup procedures. Test annually. | Critical | IT Manager / GRC Analyst | July 2026 | 0%
§164.308(a)(7)(ii)(A) | Required | Data Backup Plan | Establish procedures to create and maintain retrievable exact copies of ePHI. | Manual backups are performed but schedule is inconsistent. No offsite or cloud backup. | Partially Met | Backup process is manual and inconsistent. No offsite backup copy maintained. | Implement automated daily cloud backup. Verify backup integrity monthly. Document backup procedures. | Critical | IT Manager | May 2026 | 10%
§164.308(a)(8) | Required | Evaluation | Perform a periodic technical and nontechnical evaluation of security practices. | No formal scheduled evaluation process. Last assessment was informal and undocumented. | Not Met | No annual formal evaluation of security practices against HIPAA requirements. | Implement annual HIPAA Security Rule evaluation. Document findings. Report to leadership. | High | GRC Analyst | July 2026 | 0%
PHYSICAL SAFEGUARDS ¦ 45 CFR §164.310
§164.310(a)(1) | Required | Facility Access Controls | Implement policies and procedures to limit physical access to ePHI systems. | Server room has a basic door lock. No key card access system. No visitor log maintained. | Not Met | No key card access control on server room. No formal physical access procedures documented. | Install key card access on server room. Implement visitor log. Document physical access procedures. | High | Facilities Manager / IT Manager | July 2026 | 0%
§164.310(a)(2)(ii) | Addressable | Facility Security Plan | Implement policies and procedures to safeguard facilities from unauthorized physical access. | General building security exists but no ePHI-specific facility security plan is documented. | Partially Met | No documented facility security plan specifically addressing ePHI system locations. | Document facility security plan covering server room, workstation areas, and clinical systems. | Medium | Facilities Manager | August 2026 | 10%
§164.310(b) | Required | Workstation Use | Implement policies and procedures that specify proper functions of workstations with ePHI. | Workstation use policy exists in the AUP but workstation-specific ePHI procedures are lacking. | Partially Met | No specific procedures for workstation use in clinical areas with ePHI access. | Develop workstation use procedures for clinical areas. Include clean desk and screen lock requirements. | Medium | GRC Analyst / IT Manager | June 2026 | 10%
§164.310(c) | Required | Workstation Security | Implement physical safeguards for all workstations that access ePHI. | Workstations have automatic screen locks configured. Some clinical workstations lack privacy screens. | Partially Met | Screen lock policy in place but privacy screens not deployed in high-traffic clinical areas. | Deploy privacy screens on workstations in high-traffic areas. Verify screen lock settings on all devices. | Medium | IT Manager | July 2026 | 10%
§164.310(d)(1) | Required | Device and Media Controls | Implement policies and procedures for final disposition of ePHI and hardware on which it resides. | No formal media disposal policy. Old devices are reused or discarded without certified data destruction. | Not Met | No formal device disposal process. ePHI potentially accessible on retired hardware. | Implement certified data destruction process for all retired devices. Document disposal records. | High | IT Manager | June 2026 | 0%
TECHNICAL SAFEGUARDS ¦ 45 CFR §164.312
§164.312(a)(1) | Required | Access Control | Implement technical policies and procedures for electronic information systems containing ePHI. | Role-based access implemented in Epic EHR but not consistently enforced across all systems. | Partially Met | Access control not consistently implemented across all systems containing ePHI. | Implement role-based access control across all ePHI systems. Enforce minimum necessary access. | Critical | IT Manager | May 2026 | 10%
§164.312(a)(2)(i) | Required | Unique User Identification | Assign a unique name or number for identifying and tracking user identity. | Unique logins required in Epic EHR but some shared accounts exist on legacy systems. | Partially Met | Shared accounts identified on legacy clinical systems. Not all ePHI access is individually tracked. | Eliminate all shared accounts. Assign unique identifiers to all users on all ePHI systems. | Critical | IT Manager | May 2026 | 10%
§164.312(a)(2)(iii) | Addressable | Automatic Logoff | Implement electronic procedures that terminate an electronic session after inactivity. | Automatic logoff is configured on most workstations but not on all clinical devices. | Partially Met | Automatic logoff not consistently configured across all clinical workstations and devices. | Verify and enforce automatic logoff settings on all workstations and clinical devices. Set maximum 10 minutes. | Medium | IT Manager | June 2026 | 10%
§164.312(a)(2)(iv) | Addressable | Encryption and Decryption | Implement mechanisms to encrypt and decrypt ePHI. | Encryption applied to laptops and some servers. Email encryption for PHI not consistently enforced. | Partially Met | Email encryption for PHI transmission not consistently enforced. Some storage not encrypted. | Implement full disk encryption on all devices. Enforce encrypted email for all PHI communications. | High | IT Manager | June 2026 | 10%
§164.312(b) | Required | Audit Controls | Implement hardware, software, or procedural mechanisms to record and examine activity on systems with ePHI. | Epic EHR audit logging is enabled. Log review process is informal and infrequent. | Partially Met | Audit logs enabled but no formal review schedule or process. Anomalies may go undetected. | Formalize audit log review process. Schedule monthly reviews. Document findings and escalate anomalies. | High | Privacy Officer / GRC Analyst | May 2026 | 10%
§164.312(c)(1) | Required | Integrity | Implement policies and procedures to protect ePHI from improper alteration or destruction. | Database integrity controls exist within Epic EHR. No additional integrity monitoring in place. | Partially Met | Integrity controls limited to EHR application. No independent integrity monitoring for all ePHI systems. | Implement file integrity monitoring across all ePHI systems. Document integrity controls. | Medium | IT Manager | July 2026 | 10%
§164.312(d) | Required | Person or Entity Authentication | Implement procedures to verify that a person seeking access is who they claim to be. | Username and password authentication in place. MFA not deployed on all ePHI systems. | Partially Met | MFA not universally deployed. Authentication relies solely on password for some systems. | Deploy MFA on all systems containing ePHI. Prioritize Epic EHR and remote access. | Critical | IT Manager | May 2026 | 10%
§164.312(e)(1) | Required | Transmission Security | Implement technical security measures to guard against unauthorized access during transmission. | HTTPS used for web-based systems. Some internal transmissions not encrypted. | Partially Met | Internal network transmissions of ePHI not consistently encrypted. Email PHI sent unencrypted. | Implement TLS encryption for all internal ePHI transmissions. Enforce encrypted email for PHI. | High | IT Manager | June 2026 | 10%
ORGANIZATIONAL REQUIREMENTS ¦ 45 CFR §164.314
§164.314(a)(1) | Required | Business Associate Contracts | A covered entity must obtain satisfactory assurances from business associates that ePHI will be protected. | Some vendor contracts exist but BAA compliance has not been verified across all vendors. | Not Met | BAAs not confirmed for all vendors handling ePHI. No vendor BAA tracking process in place. | Audit all vendor contracts for BAA compliance. Obtain missing BAAs. Implement vendor BAA tracker. | Critical | GRC Analyst / Legal | May 2026 | 0%
POLICIES AND PROCEDURES ¦ 45 CFR §164.316
§164.316(a) | Required | Policies and Procedures | Implement reasonable and appropriate policies and procedures to comply with HIPAA Security Rule. | Some policies exist but are incomplete and not consistently enforced or reviewed. | Partially Met | Policy suite is incomplete. Existing policies not reviewed on a regular schedule. | Complete policy suite development. Implement annual policy review schedule. Track acknowledgments. | High | GRC Analyst / CISO | June 2026 | 10%
§164.316(b)(1) | Required | Documentation | Maintain written security policies and procedures and retain for 6 years. | Documentation is scattered and not centrally managed. Retention policy not enforced. | Not Met | No centralized document management. Retention period for security documentation not enforced. | Implement centralized document management system. Apply 6-year retention policy to all security documentation. | High | GRC Analyst | July 2026 | 0%
CONFIDENTIAL ¦ White Plains Hospital GRC Program ¦ Nadhir Choudhury ¦ Educational purposes only

## Remediation Roadmap
WHITE PLAINS HOSPITAL ¦ HIPAA GAP REMEDIATION ROADMAP ¦ April 2026
IMMEDIATE — 30 Days ¦ April to May 2026 ¦ 4 items
Priority | HIPAA Section | Control Name | Remediation Action | Owner | Status | Target Date | Notes
Critical | §164.308(a)(1)(ii)(A) | Risk Analysis | Conduct formal annual risk assessment. Document findings in risk register. Report to leadership. | GRC Analyst | Not Met | April 2026 | Risk analysis scoping initiated. Assign GRC Analyst as lead by April 15.
Critical | §164.308(a)(6)(i) | Security Incident Procedures | Develop formal incident response plan. Define roles, procedures, and communication protocols. Conduct tabletop exercise. | GRC Analyst / CISO | Not Met | May 2026 | IRP template selected. Draft due May 15. Tabletop exercise scheduled June 2026.
Critical | §164.308(a)(7)(i) | Contingency Plan | Develop contingency plan with defined RTO and RPO. Document backup procedures. Test annually. | IT Manager / GRC Analyst | Not Met | July 2026 | INITIATE IMMEDIATELY — RTO/RPO scoping by April 30. Full plan delivery July 2026.
Critical | §164.314(a)(1) | Business Associate Contracts | Audit all vendor contracts for BAA compliance. Obtain missing BAAs. Implement vendor BAA tracker. | GRC Analyst / Legal | Not Met | May 2026 | Vendor contract list pulled. BAA audit in progress. Tracker template created.
SHORT TERM — 60 Days ¦ May to June 2026 ¦ 9 items
Priority | HIPAA Section | Control Name | Remediation Action | Owner | Status | Target Date | Notes
Critical | §164.308(a)(1) | Security Management Process | Establish formal security management program. Document all policies. Create quarterly review schedule. | CISO / GRC Analyst | Partially Met | May 2026 | Policy framework selected (NIST CSF). Drafting begins May 2026.
Critical | §164.308(a)(1)(ii)(B) | Risk Management | Create and maintain formal risk register. Document treatment plans for all identified risks. | GRC Analyst | Partially Met | May 2026 | Risk register template complete. Population from gap assessment underway.
Critical | §164.308(a)(5)(i) | Security Awareness and Training | Expand training program to include cybersecurity awareness. Add phishing simulation exercises quarterly. | HR Manager / GRC Analyst | Partially Met | May 2026 | LMS vendor selected. Phishing simulation vendor evaluated.
Critical | §164.308(a)(5)(ii)(B) | Protection from Malicious Software | Deploy enterprise EDR solution. Implement malware awareness in training program. Establish reporting procedure. | IT Manager | Partially Met | June 2026 | EDR vendor shortlist created. Procurement approval pending.
Critical | §164.308(a)(5)(ii)(D) | Password Management | Enforce password policy technically on all systems. Implement MFA. Deploy enterprise password manager. | IT Manager | Partially Met | May 2026 | Password policy updated. MFA deployment plan drafted.
Critical | §164.308(a)(7)(ii)(A) | Data Backup Plan | Implement automated daily cloud backup. Verify backup integrity monthly. Document backup procedures. | IT Manager | Partially Met | May 2026 | Cloud backup vendor selected. Automated backup configured.
Critical | §164.312(a)(1) | Access Control | Implement role-based access control across all ePHI systems. Enforce minimum necessary access. | IT Manager | Partially Met | May 2026 | RBAC matrix being designed for Epic EHR and key systems.
Critical | §164.312(a)(2)(i) | Unique User Identification | Eliminate all shared accounts. Assign unique identifiers to all users on all ePHI systems. | IT Manager | Partially Met | May 2026 | Shared account audit complete. 3 accounts identified for remediation.
Critical | §164.312(d) | Person or Entity Authentication | Deploy MFA on all systems containing ePHI. Prioritize Epic EHR and remote access. | IT Manager | Partially Met | May 2026 | MFA rollout plan approved. Pilot group deployment May 15.
MEDIUM TERM — 90 Days ¦ June to July 2026 ¦ 16 items
Priority | HIPAA Section | Control Name | Remediation Action | Owner | Status | Target Date | Notes
High | §164.308(a)(1)(ii)(C) | Sanction Policy | Update HR disciplinary policy to include specific ePHI security violations and tiered consequences. | HR Manager / GRC Analyst | Partially Met | June 2026 | In Progress
High | §164.308(a)(1)(ii)(D) | Information System Activity Review | Implement monthly audit log review process. Assign Privacy Officer responsibility. Create review template. | Privacy Officer | Partially Met | May 2026 | In Progress
High | §164.308(a)(3)(i) | Workforce Authorization and Supervision | Implement formal written access authorization process. Document all ePHI access approvals. | IT Manager / HR Manager | Partially Met | June 2026 | In Progress
High | §164.308(a)(3)(ii)(A) | Authorization and Supervision | Create role-based access control matrix. Map each job role to minimum necessary access level. | IT Manager | Partially Met | June 2026 | In Progress
High | §164.308(a)(3)(ii)(C) | Termination Procedures | Create formal IT offboarding checklist. Automate account deactivation. Audit monthly for orphaned accounts. | IT Manager / HR Manager | Partially Met | May 2026 | In Progress
High | §164.308(a)(4)(i) | Information Access Management | Document comprehensive information access management policy with ePHI-specific requirements. | Privacy Officer / GRC Analyst | Partially Met | June 2026 | In Progress
High | §164.308(a)(4)(ii)(B) | Access Authorization | Implement formal access request and authorization workflow with documented approvals and review. | IT Manager | Not Met | June 2026 | In Progress
High | §164.308(a)(5)(ii)(C) | Log-in Monitoring | Configure automated alerts for failed login attempts and after-hours access. Assign monitoring owner. | IT Manager | Partially Met | June 2026 | In Progress
High | §164.308(a)(8) | Evaluation | Implement annual HIPAA Security Rule evaluation. Document findings. Report to leadership. | GRC Analyst | Not Met | July 2026 | In Progress
High | §164.310(a)(1) | Facility Access Controls | Install key card access on server room. Implement visitor log. Document physical access procedures. | Facilities Manager / IT Manager | Not Met | July 2026 | In Progress
High | §164.310(d)(1) | Device and Media Controls | Implement certified data destruction process for all retired devices. Document disposal records. | IT Manager | Not Met | June 2026 | In Progress
High | §164.312(a)(2)(iv) | Encryption and Decryption | Implement full disk encryption on all devices. Enforce encrypted email for all PHI communications. | IT Manager | Partially Met | June 2026 | In Progress
High | §164.312(b) | Audit Controls | Formalize audit log review process. Schedule monthly reviews. Document findings and escalate anomalies. | Privacy Officer / GRC Analyst | Partially Met | May 2026 | In Progress
High | §164.312(e)(1) | Transmission Security | Implement TLS encryption for all internal ePHI transmissions. Enforce encrypted email for PHI. | IT Manager | Partially Met | June 2026 | In Progress
High | §164.316(a) | Policies and Procedures | Complete policy suite development. Implement annual policy review schedule. Track acknowledgments. | GRC Analyst / CISO | Partially Met | June 2026 | In Progress
High | §164.316(b)(1) | Documentation | Implement centralized document management system. Apply 6-year retention policy to all security documentation. | GRC Analyst | Not Met | July 2026 | In Progress
ONGOING ¦ Quarterly Reviews ¦ 7 items
Priority | HIPAA Section | Control Name | Remediation Action | Owner | Status | Target Date | Notes
Medium | §164.308(a)(2) | Assigned Security Responsibility | Document formal security responsibility assignments. Establish GRC Analyst role with defined responsibilities. | CISO | Partially Met | May 2026 | In Progress
Medium | §164.308(a)(3)(ii)(B) | Workforce Clearance Procedure | Implement quarterly user access reviews. Verify access remains appropriate for current job function. | HR Manager / IT Manager | Partially Met | July 2026 | In Progress
Medium | §164.310(a)(2)(ii) | Facility Security Plan | Document facility security plan covering server room, workstation areas, and clinical systems. | Facilities Manager | Partially Met | August 2026 | In Progress
Medium | §164.310(b) | Workstation Use | Develop workstation use procedures for clinical areas. Include clean desk and screen lock requirements. | GRC Analyst / IT Manager | Partially Met | June 2026 | In Progress
Medium | §164.310(c) | Workstation Security | Deploy privacy screens on workstations in high-traffic areas. Verify screen lock settings on all devices. | IT Manager | Partially Met | July 2026 | In Progress
Medium | §164.312(a)(2)(iii) | Automatic Logoff | Verify and enforce automatic logoff settings on all workstations and clinical devices. Set maximum 10 minutes. | IT Manager | Partially Met | June 2026 | In Progress
Medium | §164.312(c)(1) | Integrity | Implement file integrity monitoring across all ePHI systems. Document integrity controls. | IT Manager | Partially Met | July 2026 | In Progress

## Executive Dashboard
WHITE PLAINS HOSPITAL ¦ HIPAA COMPLIANCE EXECUTIVE DASHBOARD ¦ April 2026
OVERALL HIPAA SECURITY RULE COMPLIANCE STATUS
0%
NEEDS SIGNIFICANT IMPROVEMENT
Based on assessment of 36 HIPAA Security Rule requirements ¦ April 2026
COMPLIANCE STATUS BREAKDOWN
TOTAL REQUIREMENTS |  |  | MET ✅ |  |  | PARTIALLY MET ⚠️ |  |  | NOT MET ❌
36 |  |  | 0 |  |  | 27 |  |  | 9
COMPLIANCE BY SAFEGUARD CATEGORY
Safeguard Category |  |  |  | Ttl | Met | Part | N/M | Crit | %
Administrative Safeguards §164.308 |  |  |  | 20 | 0 | 15 | 5 | 9 | 0%
Physical Safeguards §164.310 |  |  |  | 5 | 0 | 3 | 2 | 0 | 0%
Technical Safeguards §164.312 |  |  |  | 8 | 0 | 8 | 0 | 3 | 0%
Organizational §164.314 |  |  |  | 1 | 0 | 0 | 1 | 1 | 0%
Policies & Procedures §164.316 |  |  |  | 2 | 0 | 1 | 1 | 0 | 0%
TOP PRIORITY FINDINGS — IMMEDIATE ACTION REQUIRED
# | HIPAA Section | Control |  | Gap Summary |  |  |  |  | Remediation Priority | Owner
1 | §164.308(a)(1)(ii)(A) | Risk Analysis |  | HIPAA requires annual documented risk analysis. No current risk assessment docum... |  |  |  |  | CRITICAL | GRC Analyst
2 | §164.308(a)(6)(i) | Security Incident Procedures |  | No documented incident response plan. Staff do not know escalation procedures. |  |  |  |  | CRITICAL | GRC Analyst / CISO
3 | §164.308(a)(7)(i) | Contingency Plan |  | No documented contingency plan. No defined RTO or RPO. Backup procedures unteste... |  |  |  |  | CRITICAL | IT Manager / GRC Analyst
4 | §164.314(a)(1) | Business Associate Contracts |  | BAAs not confirmed for all vendors handling ePHI. No vendor BAA tracking process... |  |  |  |  | CRITICAL | GRC Analyst / Legal
CONFIDENTIAL ¦ White Plains Hospital GRC Program ¦ Nadhir Choudhury ¦ Educational purposes only